## Slide 1
AI Transformation Portfolio
Leadership brief · status period ending 16 October 2026 · 8 initiatives
ASSESSED STATUS
1 Green
5 Amber
2 Red
Foundations are the bottleneck: Data Platform and AI Governance delays now hold up three AI go-lives. Four decisions needed by 11 Nov.
Initiative status
COMPLETE
MILESTONE TO WATCH (FORECAST)
Data Platform
DAT-02
55%
Customer domain live: 31 Mar +75d
AI Governance
GOV-03 · reported Amber
60%
Customer-facing GenAI checklist approved: 11 Nov +42d
CS Copilot
CRM-01
45%
Wave 2 go-live (350 agents): 7 Dec +35d
Skills Academy
HR-05 · reported Green
65%
Responsible AI module live (mandatory): 29 Jan +89d
Identity & Access
IT-07 · reported Green
75%
Partner B2B identity live: 31 Jan +61d
Proposal Generator
SAL-08
35%
Customer-facing approval (GOV-03): TBC (was 30 Nov)
Demand Forecasting
SCM-06
40%
Full-range training data available: 4 Dec +49d
Invoice Automation
FIN-04
70%
STP rate ≥ 70%: 29 Jan +29d
Top risks ranked by impact across the portfolio
SCORE
1
Product catalogue delay stalls three AI go-lives
Copilot wave 2 slips to December and forecasting may miss the S/S 2027 cycle (~€1M benefit deferred ~6 months); losing contractors on 31 Oct pushes the catalogue into January.
Root: DAT-02 · Hits: CRM-01, SCM-06, SAL-08
44
2
Governance capacity blocks customer-facing AI
No customer-facing GenAI go-live before 11 Nov at the earliest; the €1.4M proposal benefit is on hold and mandatory Responsible AI training slips into 2027.
Root: GOV-03 · Hits: CRM-01, SAL-08, HR-05
44
3
Users bypass AI output; training timing drifts
Benefits depend on agents and planners acting on AI output; training booked against moving go-live dates will need rebooking and won't stick.
Root: HR-05 · Hits: CRM-01, SCM-06, SAL-08
16
4
2027 AI run costs rising across vendors
A 12% document-AI price rise, ~10% model token uplift, the unfunded €65k sandbox and €90k app upgrades all land in 2027.
Root: FIN-04 · Hits: CRM-01, HR-05, IT-07
14
5
AI compliance gaps: monitoring and shadow AI
Manual monitoring won't scale past ~10 production use cases, and unknown AI inside third-party SaaS creates EU AI Act exposure.
Root: GOV-03
12
Decisions needed
1
CFO: approve the Data Platform contractor SOW extension by 24 Oct
2
Sponsor: confirm Copilot wave 2 waits for the new knowledge index (7 Dec) so training is rebooked by 25 Oct
3
Product Management: release 3 FTE for a six-week data quality sprint, SKU mapping first
4
Exec committee: fund a Responsible AI lead and a joint CRM-01/SAL-08 checklist dry run before 11 Nov
Source: 8 status reports (15 pages), summarised by LLM (replay of reference_run). Risk score = likelihood × impact × (1 + 0.25 per other initiative hit). RAG is the assessed view; where it differs from the team's report, the reported status is shown.
Notes: KEY MESSAGES
1. Value is proven where AI is live: invoice automation runs 64% touch-free and the service copilot cuts handle time 11% in pilot.
2. Delivery risk has moved to the foundations: the product catalogue (DAT-02) and the customer-facing AI checklist (GOV-03) together block CS Copilot, Demand Forecasting and the Proposal Generator.
3. Both bottlenecks are capacity problems with small fixes: a contractor extension and 3 product FTE for data, one Responsible AI lead for governance.
PORTFOLIO RISKS (ranked)
#1 [43.8] Product catalogue delay stalls three AI go-lives — root DAT-02
Impact: Copilot wave 2 slips to December and forecasting may miss the S/S 2027 cycle (~€1M benefit deferred ~6 months); losing contractors on 31 Oct pushes the catalogue into January.
Action: CFO approves contractor SOW extension by 24 Oct; Product Management releases 3 FTE for data quality; DAT-02 delivers the SKU mapping table first.
Rolls up: DAT-02.R1, DAT-02.R2, DAT-02.R3, CRM-01.R1, SCM-06.R1, SCM-06.R2, SAL-08.R2
#2 [43.8] Governance capacity blocks customer-facing AI — root GOV-03
Impact: No customer-facing GenAI go-live before 11 Nov at the earliest; the €1.4M proposal benefit is on hold and mandatory Responsible AI training slips into 2027.
Action: Exec committee funds a Responsible AI lead; run a joint CRM-01/SAL-08 checklist dry run before the 11 Nov approval meeting.
Rolls up: GOV-03.R1, GOV-03.R2, GOV-03.R5, CRM-01.R2, SAL-08.R1, HR-05.R1
#3 [15.8] Users bypass AI output; training timing drifts — root HR-05
Impact: Benefits depend on agents and planners acting on AI output; training booked against moving go-live dates will need rebooking and won't stick.
Action: Lock go-live dates before booking training; extend the champions network to supply chain planners.
Rolls up: CRM-01.R4, SCM-06.R3, HR-05.R2, HR-05.R3, SAL-08.R4
#4 [14.0] 2027 AI run costs rising across vendors — root FIN-04
Impact: A 12% document-AI price rise, ~10% model token uplift, the unfunded €65k sandbox and €90k app upgrades all land in 2027.
Action: Consolidate AI run costs into one 2027 budget line; Procurement negotiates the FIN-04 renewal before March.
Rolls up: FIN-04.R2, CRM-01.R5, HR-05.R4, IT-07.R3
#5 [12.0] AI compliance gaps: monitoring and shadow AI — root GOV-03
Impact: Manual monitoring won't scale past ~10 production use cases, and unknown AI inside third-party SaaS creates EU AI Act exposure.
Action: Fund monitoring tooling in the 2027 budget round; Procurement adds AI questions to vendor onboarding by end of November.
Rolls up: GOV-03.R3, GOV-03.R4
#6 [12.0] Legacy warehouse renews at ~€420k — root DAT-02
Impact: If migrations miss 1 Mar 2027, the old warehouse licence renews for another year at about €420k.
Action: Take a go/no-go on decommission in January from the customer-domain forecast; negotiate a short extension option now.
Rolls up: DAT-02.R4
#7 [11.2] Partner identity delays copilot for Tallinn — root IT-07
Impact: Outsourced agents go live 1 Feb 2027 at the earliest instead of 11 Jan.
Action: CISO chooses the interim partner-identity option this month.
Rolls up: IT-07.R1, CRM-01.R3
RAG CHANGES (reported -> assessed)
GOV-03: AMBER -> RED. Self-assessed Amber, but the customer-facing checklist has slipped three times, now blocks two go-lives, and the capacity cause is unresolved.
HR-05: GREEN -> AMBER. Enrolment is ahead of plan, but the mandatory Responsible AI module (an AI-literacy compliance item) slips to 2027 and copilot training dates are unconfirmed.
IT-07: GREEN -> AMBER. Reported 'GREEN-ish', but partner identity has slipped two months, delaying a dependent rollout, and the access-request SLA is being breached.